## Sheet1
RISK ASSESSMENT
Risk Assessment No. |  | SHFT-001-RA- Working at Heights | Date: 30/10/15 | HARBOUR TRUST
Location: |  | Cockatoo Island - Building No. 14 |  |  | Task to be completed |  | Fixing metal roof sheeting on the south end of building
A Formal Risk Assessment is to be completed (where required) for; complex tasks, tasks involving more than one contractor, large projects or where ever it is deemed necessary. Do not proceed with this task if you do not feel safe to do so
AUTHOR / S | No. OF TASK STEPS | TASK | RISK / HAZARD | OUTCOME | RISK RATING (Inherent risk) | CONTROLS | RISK RATING (Residual Risk) | RESPONSIBLE PERSON | ADDITIONAL INFORMATION
T. Lulham / S. Brothers | 1 | Nailing metal sheeting to roof | Falling off roof | Serious injury / death | 5 | 1. Harness must be worn 2. Anchor points to be checked and are to be appropriate 3. Static line to be implemented if required 4. Testing & tagging of all fall arrest equipment to be current and evident 5. Worker to be WAH trained 6. WAH Permit to be completed and signed 7. All tooling & equipment to be contained or on lanyards 8. Supervision | 3 | Building & Site Services Manager | 1. SHFT-001-PRO-Working at Heights Procedure 2. SHFT-001-FOR-Working at Heights Permit 3. Parkland Induction 4. Task to be monitored
Once you have completed the risk assessment follow the residual risk ranking (when controls have been implemented) protocol as per below:
| Stop work immediately task cannot be completed |  | Stop work immediately change the task to eliminate the risk. |  | Controls are to be monitored during the task |  |  | Controls are effective
Name of person / s completing the risk assessment: |  |  |  | Company Name: |  |  | Signature:
Name of person / s completing the risk assessment: |  |  |  | Company Name: |  |  | Signature:
Name of person / s completing the risk assessment: |  |  |  | Company Name: |  |  | Signature:
Name of person / s completing the risk assessment: |  |  |  | Company Name: |  |  | Signature:
Name of person / s completing the risk assessment: |  |  |  | Company Name: |  |  | Signature:
If you are unsure of how to control the risk and need assistance contact your Harbour Trust Supervisor before commencing any work
Description of how to use the Risk Matrix is on pages 5 & 6 Incident Investigation Procedure
the author is the person who writes the RA
Number each step as you go ( this is not normally the first step it is just an example)
What is the actual task being conducted?
What is the risk or hazard of that task?
What is the outcome should that occur?
What is the worst possible out come that could occur by completing that task? (inherent risk)
What controls can be put in place to eliminate the risk of that worker falling ?
What is the level of risk (residual) once controls have been put into place?
Who is responsible for the work that is being conducted and to ensure the correct procedures are followed?
What else is in place to assist in the control of the risk?
Severe
High
Medium
Low
All RA are to entered onto a register (Safety)

## Sheet3
Drop Down Lists
Risk Treatment
Yes
No
Risk Registers
Acc | Accommodation | TBC
SHFT | Harbour Trust
AMO | Asset Management & Operations
CIT | Corporate Services & IT | TBC
Fin | Finance
HRV | Human Resources & Volunteers
LPM | Leasing & Property Management
Mkt | Marketing & Customer Experience
Risk Categories
Financial
WHS |  | Added for Strategic RR
People |  | Added for Strategic RR
Stakeholders |  | Added for Strategic RR
Asset Management |  | Added for Strategic RR
Knowledge
Legal/Regulatory
Natural
Operational |  | HC moved to PEOPLE
Other/TBC |  | TBD
Strategic
Public Safety
People
Safety/People
Stakeholders
Asset Management